## GANTT CHART
TASK NAME | START DATE | DURATION | DEPENDENCY
DEFINE EVENT GOALS | 2023-08-01 | 2 | 0
CREATIVE EVENT GOALS | 2023-08-03 | 5 | 1
DESIGN EVENT BRANDING | 2023-08-08 | 7 | 2
DEVELOP EVENT WEBSITE | 2023-08-11 | 8 | 5
PLAN MARKETING STRATEGY | 2023-08-13 | 3 | 1
EXECUTE MARKETING CAMPAIGN | 2023-08-17 | 10 | 4
SPONSORSHIP EVENT | 2023-08-21 | 3 | 2
GANTT CHART

## description
GIANTT CHART DESCRYPTION
A Gantt chart is a powerful tool that helps in project planning and tracking by providing a visual representation of tasks, timelines, and dependencies. It allows everyone to effectively plan, schedule, and monitor progress throughout the project lifecycle.This benefits company to keep a track of operations going on.
1.)Visual Representation: A Gantt chart presents project information in a more visulaize, clear and easy-to-understand manner.
2.)Task Dependencies: In a Gantt chart, you can establish dependencies between tasks, indicating which tasks need to be completed before others can start.
3.)Timeline Visualization: By representing tasks and their durations in a Gantt chart, you can easily identify project milestones and deadlines.
4.)Progress Tracking: Gantt charts enable project teams to track the progress of each task in real-time.